## 2023-2024 Gantt Chart
Item | Description | 2023 | [8 empty] | 2024
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Modelling / Analysis Iteration 1
1.1 | Agree inputs, parameters and assumptions | bar: 2023 Sep to 2023 Oct
1.2 | Core pathways development and modelling | bar: 2023 Oct to 2023 Nov
1.3 | Paris Test Assessment | bar: 2023 Nov
1.4 | Additional modelling and testing of results | bar: 2023 Nov to 2023 Dec
1.5 | Post-hoc analysis | bar: 2023 Dec to 2024 Jan
2 | Modelling / Analysis Iteration 2
2.1 | Agree inputs, parameters and assumptions | bar: 2024 Feb to 2024 Mar
2.2 | Core pathways development and modelling | bar: 2024 Mar to 2024 Apr
2.3 | Paris Test Assessment | bar: 2024 Apr
2.4 | Additional modelling and testing of results | bar: 2024 Apr to 2024 May
2.5 | Post-hoc analysis | bar: 2024 May to 2024 Jun
3 | Modelling / Analysis Iteration 3
3.1 | Agree inputs, parameters and assumptions | bar: 2024 Jul
3.2 | Core pathways development and modelling | bar: 2024 Jul to 2024 Aug
3.3 | Paris Test Assessment | bar: 2024 Aug
3.4 | Additional modelling and testing of results | bar: 2024 Aug to 2024 Sep
3.5 | Post-hoc analysis | bar: 2024 Aug to 2024 Sep
4 | Research/Consultancy
4.1 | Review of international approaches to carbon budgets | bar: 2023 Apr
4.2 | Pathways to 2050 | bar: 2023 Oct to 2023 Dec
4.3 | Macroeconomic Impacts of the Transition (TBC) | bar: 2023 Aug to 2024 Aug
4.4 | Paris Test (TBC) | bar: 2023 Nov to 2023 Dec; 2024 Apr to 2024 May; 2024 Aug to 2024 Sep
4.5 | Marine biodiversity impacts of offshore wind (TBC) | bar: 2024 Jan to 2024 Mar; 2024 Aug to 2024 Sep
4.6 | Effects of new forestry targets on biodiversity (TBC) | bar: 2024 Jan to 2024 Mar; 2024 Aug to 2024 Sep
4.7 | Just Transition Research (TBC) | bar: 2024 Jan to 2024 Mar; 2024 Aug to 2024 Sep
A | Key Inputs
A.1 | 2023 Greenhouse Gas Projections (EPA) | bar: 2023 May
A.2 | 2023 Provisional Inventories (EPA) | bar: 2023 Jun to 2023 Jul
A.3 | Ireland's National Inventory Submissions 2024 (EPA) | bar: 2024 Mar
A.4 | 2024 WEM/WAM Projections (EPA) | bar: 2024 Apr to 2024 May
A.5 | 2024 Provisional Inventories (EPA) | bar: 2024 May to 2024 Jun
A.6 | Land Use Review | bar: 2023 Jul to 2023 Sep
A.7 | Ireland’s Long Term Climate Strategy (DECC) | bar: 2023 Oct to 2023 Dec
A.8 | Intercensal Population Estimates (2017-2023) (CSO) | bar: 2023 Sep
A.9 | National Population and labor Force Projections (CSO) | bar: 2024 Apr to 2024 Jun
A.10 | ESAB Input to the proposal of a EU target for 2040 and 2030-2050 greenhouse gas budget (ESAB) | bar: 2023 Apr to 2023 Jun
A.11 | Proposal for EU 2040 climate target (EC) | bar: 2024 Jan to 2024 Jun
A.12 | Conclusion of Global Stocktake (COP28) | bar: 2023 Dec
D | Key Deliverables
D.1 | Modelling / Analysis Iteration 1 Results | bar: 2024 Jan
D.2 | Modelling / Analysis Iteration 2 Results | bar: 2024 Jun
D.3 | Modelling / Analysis Iteration 3 Results | bar: 2024 Sep
D.4 | Carbon Budgets Technical Report | bar: 2024 Sep to 2024 Nov
D.5 | CCAC Carbon Budget Proposals | bar: 2024 Dec

## Preparatory work
Description | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Preparatory Work

## CB WG Meetings
CB WG Meeting No. | Proposed Date and Time | Topic(s) for Consideration
1 | Thursday 9th March 2023 10:00 – 13:00 | Carbon Budgets Methodology
2 | Thursday 20th April 2023 13:30 – 16:30 | Carbon Budgets Methodology / Scoping of modelling work
3 | Wednesday 31st May 2023 10:30 – 13:30 | Vision for 2050 and Beyond/ Scoping of modelling work/ International approaches to carbon budgets
4 | Thursday 29th June 2023 13:30 – 16:30 | Climate Justice and ‘Paris Test’/ Macroeconomic Impacts of carbon budgets
5 | Thursday 27th July 2023 13:30 – 16:30 | Focused discussion on methane/ Socioeconomic considerations
6 | Friday 8th September 2023 13:30 – 16:30 | Biodiversity Considerations/ Populations Projections (CSO)
CB WG Workshop 1 | Week 2 September 2023 (TBC) | Input model parameters for 2030 starting points, scenario development and assumptions
7 | Thursday 19th October 2023 13:30 – 16:30 | Landuse Review/ 2024 Projections Process (EPA, SEAI & ESRI)
8 | Thursday 23rd November 2023 10:30 – 13:30 | Role of Negative Emissions/ TBC
9 | Friday 15th December 2023 13:30 – 16:30 | TBC
10 | Q1 2024 (TBC) | TBC
11 | Q1 2024 (TBC) | TBC
CB WG Workshop 2 | Q1 2024 (TBC) | TBC
12 | Q1 2024 (TBC) | TBC
13 | Q2 2024 (TBC) | TBC
14 | Q2 2024 (TBC) | TBC
15 | Q2 2024 (TBC) | TBC
16 | Q3 2024 (TBC) | TBC
17 | Q3 2024 (TBC) | TBC
18 | Q3 2024 (TBC) | TBC

## Risk Register
ID | Date Raised | Risk Description | Likelihood of the risk occurring | Impact if the risk occurs | Severity (rating based on likelihood and impact) | Mitigating Action | Progress on Actions | Status
1 | 20/03/23 | Revision of carbon budgets, as provided for under Section 6D of the Act | Medium | Medium | Medium | The Minister, at any stage, can request a revision of carbon budgets as provided for under Section 6D of the Act. The potential for the minister to request a revision of carbon budgets has been reflected in both the Carbon Budgets Methodology and the Terms of Reference for the Carbon Budgets Working Group. The role of the Carbon Budgets Working Group in responding to any request from the Minister to the Council for a review will be determined by Council if it arises. | Ongoing Monitoring | Open